# Proposed Implementation Timeline

Online Job Offer System  |  One Full-Stack Developer  |  Baseline: 30 Weeks

Version 1.0  •  21 July 2026

# Executive Summary

A practical baseline is 30 calendar weeks from approved kickoff to production handover for one dedicated full-stack developer. The plan sequences the highest-risk foundations first—data model, access control, salary rules, proposal versioning, and approval routing—then completes candidate outcomes, documents, reporting, integration testing, UAT, and deployment.

| Planning Item | Proposed Position |
| --- | --- |
| Recommended baseline | 30 weeks |
| Target MVP feature-complete | End of Week 23 |
| System/UAT stabilization | Weeks 24-28 |
| Production release | Week 30 |
| Delivery capacity assumption | 1 developer, ~80% planned delivery capacity |
| Estimate confidence | Planning estimate; refine after discovery and technical platform confirmation |

# Scope Basis

The estimate covers the end-to-end workflow described in the supplied sources: candidate intake through MS Forms, validation, legal-entity salary matrix selection, one-to-three proposal options, salary-band calculations, per-option approval decisions, President escalation for above-band offers, reminders/escalations, candidate discussion and re-proposal, offer-letter generation, delegation, audit history, governance reporting, and role-based access.

# Delivery Timeline at a Glance

| Phase | W1-3 | W4-6 | W7-9 | W10-12 | W13-15 | W16-18 | W19-21 | W22-24 | W25-27 | W28-30 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Discovery & architecture | ● |  |  |  |  |  |  |  |  |  |
| 2. Platform foundation | ● | ● |  |  |  |  |  |  |  |  |
| 3. Candidate intake |  | ● | ● |  |  |  |  |  |  |  |
| 4. Salary analysis |  |  | ● | ● |  |  |  |  |  |  |
| 5. Approval workflow |  |  |  |  | ● | ● |  |  |  |  |
| 6. Candidate outcome & documents |  |  |  |  |  | ● | ● |  |  |  |
| 7. Reporting & administration |  |  |  |  |  |  | ● | ● |  |  |
| 8. System hardening |  |  |  |  |  |  |  | ● | ● |  |
| 9. UAT & release readiness |  |  |  |  |  |  |  |  | ● | ● |
| 10. Go-live & hypercare |  |  |  |  |  |  |  |  |  | ● |

# Detailed Phase Plan

| # | Weeks | Workstream | Key Activities | Exit Deliverable | Scope Trace |
| --- | --- | --- | --- | --- | --- |
| 1 | W1-2 | Discovery & solution architecture | Confirm platform, integrations, non-functional needs, workflow states, roles, data model, environments, backlog and acceptance approach. | Approved solution outline; prioritized backlog; architecture/data model; delivery setup | All; BL-01 to BL-20 |
| 2 | W3-5 | Foundation, security & master data | Project skeleton, database migrations, authentication, RBAC/ABAC, legal entities, requisitions, users, approver matrix, salary-matrix administration and audit framework. | Working secured application; core master-data screens/APIs; CI/CD baseline | US-04, US-16, US-19; BL-01, 04-05, 17-18 |
| 3 | W6-8 | Candidate intake & validation | Create job-offer case, MS Forms handoff/import approach, file validation/storage, submission tracking, correction loop and TA validation. | Traceable candidate intake; validated package workflow | US-01 to US-03 |
| 4 | W9-12 | Salary analysis & proposal engine | Effective-dated matrix lookup; 1-3 proposal options; compa-ratio, increase and band-position calculations; exception flags; proposal version model. | Job Offer Analysis with reliable calculations and validation | US-04 to US-06, US-13, US-19; BL-05 to 09 |
| 5 | W13-17 | Approval routing & notifications | Per-option decisions, HROD/Division approval, President escalation, rejection comments, secure task links, email/in-app notices, reminders, escalation, retries and delivery logs. | End-to-end approval workflow with SLA handling | US-07 to US-11, US-20, US-21; BL-10 to 12, 19 |
| 6 | W18-20 | Candidate decision, re-proposal & offer letter | Approved-options-only discussion, accept/decline/negotiation, new proposal cycles with history, final offer merge and secure document storage. | Candidate outcome workflow; generated offer letter | US-12, US-13, US-15; BL-13 to 16 |
| 7 | W21-23 | Delegation, dashboards & governance | Delegate/reassign/shadow access, transaction history, HRBP status view, above-band report, filters/export and administration refinements. | Feature-complete MVP; operational dashboards and reports | US-14, US-16 to US-18; BL-17, 18, 20 |
| 8 | W24-26 | Integration, security & system testing | End-to-end scenarios, negative paths, authorization checks, audit reconciliation, file security, notification failures, performance checks, backups and defect repair. | Release candidate; system test evidence; operating notes | All stories and business rules |
| 9 | W27-29 | UAT, remediation & release readiness | Business-led UAT, developer fixes, regression, data/config preparation, user/admin guidance, deployment rehearsal and go-live approval. | UAT sign-off; deployment package; support runbook | All acceptance criteria |
| 10 | W30 | Production deployment & hypercare | Production release, smoke tests, monitoring, priority defect response, handover and backlog closure review. | Live system; handover; post-launch backlog | All |

# Milestones and Decision Gates

| Gate | Target | Milestone | Exit Criteria |
| --- | --- | --- | --- |
| M1 | End W2 | Scope and architecture approved | Platform/integration decisions and backlog are sufficiently clear to build. |
| M2 | End W8 | Intake workflow demo | TA can create a case, receive/validate candidate inputs, and see an auditable status history. |
| M3 | End W12 | Salary engine demo | Matrix lookup, calculations, band flags, and proposal versioning pass agreed examples. |
| M4 | End W17 | Approval workflow demo | Normal and above-band paths, per-option decisions, reminders, and escalation work end to end. |
| M5 | End W23 | Feature complete | All planned user stories are available in the test environment. |
| M6 | End W26 | Release candidate | System, security, and end-to-end tests pass with no open critical defects. |
| M7 | End W29 | Go-live approval | UAT signed off; configurations, deployment and support materials are ready. |
| M8 | W30 | Production handover | Smoke tests pass and ownership transfers to operations/support. |

# Planning Assumptions

The developer is allocated full time, with approximately 80% of capacity available for planned delivery after ceremonies, support and rework.

A product owner and representatives from TA, Total Rewards, HROD, HRBP, Division leadership and IT/security are available for weekly clarification and scheduled reviews.

A supported application platform, identity provider, email service, database, document storage and deployment environment are selected by the end of Week 2.

MS Forms integration is limited to a supported handoff/import/API pattern; building a new public candidate portal is outside this baseline.

One offer-letter template and one primary notification channel configuration are included initially; extensive template variants or Teams integration require re-estimation.

Business users supply approved salary matrices, approver mappings, SLA thresholds, legal entities, test data and offer templates on schedule.

UAT execution is performed by business users; the developer supports triage, remediation and regression.

Calendar duration excludes major organizational shutdowns and assumes stakeholder decisions are returned within two business days.

# Dependencies and Schedule Risks

| Rating | Risk / Dependency | Schedule Effect | Mitigation |
| --- | --- | --- | --- |
| High | Late platform/integration decisions | Delays architecture and can cause rework across intake, notifications and deployment. | Confirm technical stack and service owners in Week 1; time-box proof-of-concept work. |
| High | Unavailable or changing salary/approval rules | Blocks calculation and workflow acceptance. | Obtain approved matrices and decision tables by Week 3; version all rule changes. |
| High | Single-developer concentration | Illness, production support or competing work directly affects the critical path. | Protect allocation, document weekly, automate tests/deployment, and keep a visible contingency backlog. |
| Medium | Identity, email, storage or MS Forms access | External approvals and tenant configuration can create idle time. | Raise access requests during discovery and use stubs/mocks until credentials arrive. |
| Medium | Slow stakeholder review/UAT | Defects and rule gaps surface late. | Run demos at M2-M5 and book UAT participants before Week 23. |
| Medium | Security/privacy findings | Compensation and candidate documents require strict access and auditability. | Threat-model early; test role boundaries and document access before UAT. |

# Estimate Boundaries and Change Control

The 30-week baseline is appropriate for planning and sequencing, but it is not a fixed-price commitment. Re-estimate after Week 2 when the platform, integration pattern, security constraints, document templates and reporting expectations are confirmed. Add schedule or trade scope when requirements introduce a public candidate portal, complex legacy migration, multiple offer-letter variants, e-signature, Microsoft Teams integration, advanced analytics, high-availability requirements, or material policy changes.

# Recommended Working Cadence

| Frequency | Activity |
| --- | --- |
| Weekly | Backlog refinement and stakeholder decision session |
| Every 2 weeks | Demonstration, acceptance review and next-sprint commitment |
| Continuous | Automated unit/integration checks, audit logging and deployment pipeline |
| At each milestone | Formal exit review against the gate criteria above |
| Weeks 27-29 | Structured UAT cycles with daily defect triage |

# Source References

Online Job Offer System - User Stories V2.xlsx

Job Offer Business Logic Rules.docx

Job Offer Programmer Detailed Flowchart - Editable Text.docx

Prepared as a proposed delivery baseline. Dates should be converted from relative weeks to calendar dates after kickoff is approved.

NOTE: 
July 24 – start Dev

Target GO Live – Sept 28